# Progress Report on matters raised at previous meetings as at 20.11.25

| Item | Minute No. | Update |
| --- | --- | --- |
| Highways issues | 357/22 406/23 | Wem Traffic Project new Unitary Councillors to be asked to continue to push for traffic impact assessment to be included in a future Shropshire Council capital budget |
| Wilmott Meadow | 112/18 | Taylor Wimpey progressing legal transfer of phase 1 POS. Awaiting section 38 agreement with Shropshire Council for the storm drains to be completed before the public open space transfer can take place. Chased again May 25 Taylor Wimpey still awaiting adoption completion by Shropshire Council |
| Climate change | 648/24 793/24 | Climate Change Action Plan updated and on website |
| Public Toilets |  | No major issues over summer, time clock for lights currently broken in car park toilets, quote for repair and installation of LED lights with PiR sensors awaited |
| Streetlighting | 44/25-29 103/25-26 | Column replacement to take place in New Year – residents in Eckford Park informed of delay Tender currently advertised as per the regulations. |
| Events Christmas Festival Carols | 888/25 41/25-29b | On agenda 17.12.25 |
| Mayoral chain | 890/25 | Not updated as per 890/25 Deputy Mayor’s bar engraved |
| Jubilee Square Tree | 891/25 | £600 earmarked prior to year end closedown to be planted in New Year |
| Christmas Lights | 24/25-29a | Competition winning entry designed and presentation made 17.11.25 |
| Lowe hill Development | 59/25-29c | Email sent ref meeting about commuted sum 1.8.25 no response to date |
| Policing Panel and PCC Survey | 70/25-29 | Survey sent Names of Councillors on panel provided no update on meeting date |
| LNRS Local Nature Recovery Scheme Cluster Group | 71/25-29 | Response sent 1.8.28, conference attended 3.10.25 with Cllr Cotterell |
| Wheatfields | 83b/25-29 | Report on agenda |
| Tree Plaque | 89/25-29 | Tree to be planted in New Year tree plaque identified |
| Inclusive play equipment | 101/25-29 | Quotes sought from 3 companies |
| Floral Planters | 102/25-29 | a) Order placed for 2026 plants c) Station Adopters to select plants to order up to value of £100 |
| Street Names for Loew Hill Development | 104/25-29 | Following names based on field names approved by Shropshire Council Hopyard Drive Clemley Place Tarver Road Brick Kiln Way Suffix’s may be altered to suit the layout of the site |
| Jubilee Square bollard | 106/25-29 | Written confirmation received from Shropshire Council that any works to repair / replace the bollards will be reimbursed as per the verbal agreement. Order to be placed. |
| Shropshire food Resilience | 106/25-29 | Survey completed on behalf of Town Council and Store Cupboard on 12.11.25 |
| Business Plan | 107/25-29 | On Website 6 monthly review needed next review April |
| Msc. |  |  |
| Allotments |  | All 66 plots at Love Lane are let with a healthy waiting list Promotion, looking to organise a seed swap in the Spring |
| Cemetery | 65/25-29 | 1 burial since last meeting Memorial inspection course took place 29.10.25. Groundsman and Facilities Officer attended |
| Market |  | New regular meat trader along with two new casual traders have started. |
| Worknest HR and H&S consultants |  | Ongoing |
| WSSA |  | Fireworks held 5.10.25. |
| CCTV |  | New Contract started camera audit underway |
| Wem Store Cupboard Project |  | Meeting held 1.10.25 |
| Wem SNT Contract | 45/25-29 | Contract to be reviewed Jan 2026 |

All general information received that does not require a decision has been circulated via email.

Diary Dates

| Date | Time | Committee / Event | Location |
| --- | --- | --- | --- |
| 29.11.25 | 13.00 | Christmas Festival | Town |
| 4.12.25 | 18.00 | WSSA Trustees | Wem library |
| 17.12.25 | 18.00 | Carols on the Green | Millenium Green |
| 18.12.25 | 19.00 | Full Council | Wem Library |
| 15.1.26 | 17.00 | Events Liaison Group (festival Review) | Wem Library |
| 21.1.25 | 14.00 | WSLC Liaison Group | Wem Library |
| 22.1.25 | 19.00 | Full Council (Budget) | Wem Library |
| 29.1.26 | 19.00 | Full Council | Wem Library |
| 26.2.26 | 19.00 | Full Council | Wem Library |
| 26.3.26 | 19.00 | Full Council | Wem Library |
| 30.4.26 | 19.00 | Full Council | Wem Library |